## Sheet1
area	Feature	Notes	Implementation detail	Testing				Days taken	Day	Priority
planning	2.6.2020							1	1	1

equip weapons										2
	units have swappable weapons	swappable by hand or other scripts	swaps happen by factory, and load from prefab/object	swap by id in inspector				0.2	2
				build simple sample ui that directly swaps the weapon on unit				0.2	2
				add that swapping option on commander				0.2	2
	ui link is new script and not directly commander		as ui-commander linker, not direct	finally, link ui to commander’s swapping.				0.2	2
	general use stats, that are used when attacking	used by combat units/ combat	allows mods or something similar	add single bonus
	get graphics for weapons			new scene, simple unit, sub pieces on unit				0	1

bonuses										3
feature	every weapon has some bonus attached		by default in prefab	attach to sample weapon&stat mods in empty scene				0.3	3
feature	Flat stat increase type		stats are added by mods	load stats from unit, when spawning weapon				0.25	4
feature	using the weapon in combat, applies the effect			see weapon mods added to unit mods				0.25	4
				test with 2 units that attack each other					4
				test for different types					4
				testi different amounts of bonuses					4
STATS
	planning for changing stats							0.3	3
	stats structure is changed and simplified to allow addition from weapons and other sources							0.25	4
	Bugfix: mods get properly added after change to stat mods script							0.3	3

units										4
	hp bar, scaled to hp		monoconnection+interface for health
	new unit – strong unit

AI										5
	enemies randomly change tactic every few seconds							0.2	2

buying										6
	buy spell or strong unit for free every 20 seconds

spells										7
	damage all enemy units over time for 5 seconds	damage only garrison-officer linked