## Sheet1
Benefit	Unexp	Optional	Feature	Description	tests	finished day	planned day
planning			08.06.2020			1	1
bigger maps			Level 1	1 map small, choke point		1	1
			Level 2	1 map medium, 2 choke points, 1 central		2	2
			Level 3	1 map large, river, 3 stations, you have 1 base, they 4			3
			level picker	pick level then enter picked level. All levels are unlocked.			2

suggestion commands			Defendable rally point	user can prioritize rally points to defend or attack from.			2
				units will respond to those requests at random intervals with certain chance.			2

unit obstacles			Hole trap	units touching this trap will fall and die instantly. Trap is invisible until first unit.			4
			Spike trap	damages and slows units that touch it			5
			Push trap	Bullet pushes the unit away.			6

weapon balance			bow adds range to unit				3
			bow reduces hp				3
			sword increases attack speed				4

unit levels			kill exp instead of time exp				5
			experiment with kill+time exp				5
			level up units				5
			exp needed is visible x/y				5

bugfix			spawning bug				6

play session			save playtime into csv.				6

unit commands	x		units will que their commands

file automation	x		csv reader	file reader for support for multiple formats		2	7