## Sheet1
area	Feature	Notes	Implementation detail	Testing				Days taken	Day	Priority
planning	2.6.2020							1	1	1

equip weapons										2
	units have swappable weapons	swappable by hand or other scripts	swaps happen by factory, and load from prefab/object	swap by id in inspector				0.2	2
				build simple sample ui that directly swaps the weapon on unit				0.2	2
				add that swapping option on commander				0.2	2
	ui link is new script and not directly commander		as ui-commander linker, not direct	finally, link ui to commander’s swapping.				0.2	2
	general use stats, that are used when attacking	used by combat units/ combat	allows mods or something similar	add single bonus
	get graphics for weapons			new scene, simple unit, sub pieces on unit				0	1

bonuses										3
feature	every weapon has some bonus attached		by default in prefab	attach to sample weapon&stat mods in empty scene
feature	Flat stat increase type		stats are added by mods	load stats from unit, when spawning weapon
feature	using the weapon in combat, applies the effect			see weapon mods added to unit mods
				test with 2 units that attack each other
				test for different types
				testi different amounts of bonuses
STATS	Note: expanded stats unregister is called from hp script
	planning for changing stats
change	stats structure is changed and simplified to allow addition from weapons and other sources
	mods get properly added after change to stat mods script
units										4
	hp bar, scaled to hp		monoconnection+interface for health
	new unit – strong unit

AI										5
	enemies randomly change tactic every few seconds							0.2	2

buying										6
	buy spell or strong unit for free every 20 seconds

spells										7
	damage all enemy units over time for 5 seconds	damage only garrison-officer linked