## Sheet1
area	Feature	Notes	Implementation detail	Testing				Days taken	Day	Priority
planning	2.6.2020							1	1	1

equip weapons										2
	units have swappable weapons	swappable by hand or other scripts	swaps happen by factory, and load from prefab/object	swap by id in inspector				0.2	2
				build simple sample ui that directly swaps the weapon on unit				0.2	2
				add that swapping option on commander				0.2	2
	ui link is new script and not directly commander		as ui-commander linker, not direct	finally, link ui to commander’s swapping.				0.2	2
	general use stats, that are used when attacking	used by combat units/ combat	allows mods or something similar	add single bonus				0.2	4
	get graphics for weapons			new scene, simple unit, sub pieces on unit				0	1

bonuses										3
feature	every weapon has some bonus attached		by default in prefab	attach to sample weapon&stat mods in empty scene				0.3	3
feature	Flat stat increase type		stats are added by mods	load stats from unit, when spawning weapon				0.2	4
feature	using the weapon in combat, applies the effect		compressor is same as adder and data	see weapon mods added to unit mods				0.2	4
				test with 2 units that attack each other
				test for different types
				testi different amounts of bonuses
STATS
	planning for changing stats							0.3	3
	stats structure is changed and simplified to allow addition from weapons and other sources							0.2	4
	Bugfix: mods get properly added after change to stat mods script							0.3	3

units										4
	hp bar, scaled to hp		monoconnection+interface for health					0.2	4

new unit
	new unit – strong unit	spawned					>5,>6
	unit heals		implement buffs				>6

AI										5
	enemies randomly change tactic every few seconds							0.2	2

buying										6
	buy spell or strong unit for free every 20 seconds						>5,>6

gameplay
+	ui for wepons	select weapons for every barract at beginning of the game						0.25	5
+	counter to select 3 weapons before resuming game							0.25	5
+	pause script to prevent comabt running in background while picking weapons		pause runner behaviours	problem with pause not begin easily globally accesible				0.25	5
+	replace movement with comabt mono							0.25	5

new spell										7
	damage all enemy units over time for some time	damage only garrison-officer linked					>5,>6