## Sheet1
Benefit	Unexp	Optional	Feature	Description	tests	finished day	planned day
planning			08.06.2020			1	1
bigger maps			Level 1	1 map small, choke point		1	1
			Level 2	1 map medium, 2 choke points, 1 central		2	2
			Level 3	1 map large, river, 3 stations, you have 1 base, they 4			3
			level picker	pick level then enter picked level. All levels are unlocked.			2

suggestion commands			Defendable rally point	user can prioritize rally points to defend or attack from. By picking mode			2
	x			single target is allowed to be active as rally. It can be picked as new tactic			2
	x			Command that stores tactical targets			2

unit obstacles			Hole trap	units touching this trap will fall and die instantly. Trap is invisible until first unit.			4
			Spike trap	damages and slows units that touch it			5
			Push trap	Bullet pushes the unit away.			6

weapon balance			bow adds range to unit				3
			bow reduces hp				3
			sword increases attack speed				4

unit levels			kill exp instead of time exp				5
			experiment with kill+time exp				5
			level up units				5
			exp needed is visible x/y				5

bugfix			spawning bug				6

play session			save playtime into csv.				6

unit commands	x		units will que their commands

file automation	x		csv reader	file reader for support for multiple formats		2	7

04:17:00 PM	checked fb on phone
04:21:00 PM	ui works, need to save it into command structure
04:23:00 PM	dozed off to some stuff about employes
04:25:00 PM	added new feature described abov
04:28:00 PM	need factory for genrating target data
04:30:00 PM	changed music to ghost in the shell
04:52:00 PM	added factory and stuff. Need to connect it
04:58:00 PM	connected to ui
05:10:00 PM	after braek wokring on ai
05:40:00 PM	rally to point is done tactic. Plus lunch. Connecting it to unit
05:55:00 PM	rally points work		done for the day