## Sheet1
Goal	‎Monday, ‎25 ‎May ‎2020,	>>
It’s an upgrade for 3 spawns 3 units system. At start pick your unit types. Pick tactics for your units. Units look like the classes they fit into.
user experience: some nice funny characters, they can command units to go back and forward, classes to make combat more interesting and bit easier to understand.

system	feature	integration	priority	Issues	time(days)	hours

customizable character
	eye art	create art, add them to prefabs as child, link as enabable
	face atr	create art, add them to prefabs as child, link as enabable
	mouth art	create art, add them to prefabs as child, link as enabable
	weapons art	create art, add them to prefabs as child, link as enabable
	caps art	create art, add them to prefabs as child, link as enabable
	link all all art pieces into array of groups of items, link the groups into one script and pick one combination randomly by function	callable from other scripts

tactics
	swappable behaviours	script on every unit, ensures that on change of behaviour, new things begins to run
	attack units, moving towards nearest unit	keep current version and wrap It
	defensive: return to base area an attack units	behavour script, connected to swappable behaviours
	defensive: attack nearby units	behaviour piece
	defensive: global area where units can head to and patrol in	behaviour piece
	attack boss	convert attack units with boss filter instead of closest enemy filter
	Ui to pick weapon for 3 characters on start	independent, in scene
gameplay
	pick default tactic for specific weapons	connect defaut tactic to character on spawn
	pick default bonuses for specific unit	connect defaut bonus to tactic on spawn
	pick tactics for you units in realtime	detaches old bonuses, adds new ones, changes behaviours
	tactics take random up to 10 seconds to take effect	delay before having effect

skill tree
	upgrades cost experience	when clicking ui also check for price	1	missing ui	1
	display cost	cost is next to upgrades			1
	display exp	and exp next to unit			1
	bug: exp isn’t subtracted correctly
	bug: levels don’t set ui to correct user