## Sheet1
Goal	‎Monday, ‎25 ‎May ‎2020,	Tuesday, 01 June 2020	8days(5working)
It’s an upgrade for 3 spawns 3 units system. At start pick your unit types. Pick tactics for your units. Units look like the classes they fit into.
user experience: some nice funny characters, they can command units to go back and forward, classes to make combat more interesting and bit easier to understand.

system	feature	integration	priority	Issues	time(days)	hours	Total	Day

tactics				some things are getting a abit mess
	swappable behaviours	script on every unit, ensures that on change of behaviour, new things begins to run		not sure what to connect It to. Where are the tactics?	0.25			2
	change combat controller to tactic controller	ui isn’t connectedable to active unit		not plannet. Make tactics swappable by hand first	0.166666666666667			3
?	pick tactic by ui			combat broke down and units don’t attack	0.166666666666667			3
?	bug: units broke down and don’t attack. They move to 0,0,0	combat wasn’t used, newly added var			0.166666666666667			3
?	combat controller has to be split up into smaller components, before making other tactics. Make Useful pieces	movement+ attacking and the actual tactics			0.166666666666667			3
?	units need to call active tactics on spawn				0.25			4
	attack units, moving towards nearest unit	keep current version and wrap It			0.166666666666667			3
	defensive: return to base area an attack units	behavour script, connected to swappable behaviours AND ally base		don’t have proper behaviour written down and proper testing	0.25			4
	Defensive will block enemy when attacking	requires structural attacking on enemies			0.25			4
	attack structure boss	convert attack units with boss filter instead of closest enemy filter			0.25			4
	ui to pick tactics	3 buttons that can be swaped at runtime, with visual indicators			0.166666666666667			3

win/lose
?	WIN LOSE UI is opened from death of unit				0.5			5
	win lose ui	got stuck on figuring out if I should create missions or just connect it to unit. Also connecting got a bit complicated.			0.5			5

skill tree							1.75
	upgrades cost experience	when clicking ui also check for price	1	missing ui	0.5			1
?	display cost	cost is next to upgrades			0.5			1
?	display exp	and exp next to unit			0.25			2
?	bug: levels don’t set ui to correct user	solution: I was loading items for displaying in no specific order, which means, they were out of order, relying on start			0.25			2
?	bug: cost nly updates when you update, not when switching user	solution: when clicking ui I didn’t add items to update. Maybe auto updater would be good.			0.25			2

customizable character
	eye art	create art, add them to prefabs as child, link as enabable
	face atr	create art, add them to prefabs as child, link as enabable
	mouth art	create art, add them to prefabs as child, link as enabable
	weapons art	create art, add them to prefabs as child, link as enabable
	caps art	create art, add them to prefabs as child, link as enabable
	link all all art pieces into array of groups of items, link the groups into one script and pick one combination randomly by function	callable from other scripts

weapons				didn’t write bonuses down
	pick weapon
	weapons have default tactic
	weapons have bonuses
	ui at start to pick weapon
cleanup
	tree data can be removed

	tactics take random up to 10 seconds to take effect	delay before having effect

	tactics on it’s own don’t hold ground
	upgrades on it’s own don’t hold ground
	together they create this sort of dynamic to it

bonuses
	like mods, add bonuses on stats, percentage