## Sheet1
Benefit	Unexp	Optional	Feature	Description	tests	planned day	finished day
planning			08.06.2020			1	1
bigger maps			Level 1	1 map small, choke point		1	1
			Level 2	1 map medium, 2 choke points, 1 central		2	2
			Level 3	1 map large, river, 3 stations, you have 1 base, they 4		3
	x		issues when adding more checkpoints	simplify sprite setup to be independent but optionally connected	automated setup to fit into ui group(context group)
			level picker	pick level then enter picked level. All levels are unlocked.		2	2
	x		exit level after winning or losing			2	2

suggestion commands			Defendable rally point	user can prioritize rally points to defend or attack from. By picking mode		2	2
	x			single target is allowed to be active as rally. It can be picked as new tactic		2	2
	x			Command that stores tactical targets		2	2

unit obstacles			Hole trap	units touching this trap will fall and die instantly. Trap is invisible until first unit.		4
They are mostly same in gameplay			Spike trap	damages and slows units that touch it		5
try to avoid			Push trap	Bullet pushes the unit away.		6

weapon balance			bow adds range to unit			3→4
				ui range display, auto load		4
				unit has range stat. Had issues with knowning function is correct with the observer/listener thingy	improve by having things watch stats instead of implementing stats	4
				prefab has stat range for bow		4
	x			found incorrect implementation of triggering on add mod events		4
	x			walk attack range isn’t connected to attack range. Fixed by stopping units		4
			bow reduces hp			3→4

might be worth keeping it			for big map the way it’s now would be faster and better
unit levels			kill exp instead of time exp			5
			experiment with kill+time exp			5
			level up units			5
			exp needed is visible x/y			5

bugfix			spawning bug			6>5

play session			save playtime into csv.			6>5

file automation	x		csv reader	file reader for support for multiple formats		7	2

changed collision	x		refactored collision trigger	it allows other scripts to be connected and triggered on collision(nonevent, object based)		4
	x		Spent 20 like minutes figuring out that i’m setting up 3d collisio layers instead of 2d.			4
	x		Had issues setting up connection to root when colliding. All so basically, separating collidable from non collidable and attackable from non attackable and who needs what collision info setup			4
	x		Traps need to be added to maps			4

changed hp	x		modified and refactored hp			4

requests	shortnames for mods that are different from displayed ui names. Basically type converting into ui content
	general addition of new stats automatically, based on excel, and not setting up objects.
	attack speed, generally making it even easier to connect new mods
	units will que their commands

playtesting	player doesn’t win on boss death